## Slide 1: Unit Meeting and Collaboration Final Presentation
Minkyung Oh
Arjun Sivanesan

## Slide 2: Initiative Overview
Briefly restate the problem, need, or opportunity your group addressed and the scope of the initiative.
Problem: Unit meetings lacked a standardized onboarding process leading faculty and researchers to having different working expectations, this led to:
  Inconsistent expectations
  Duplicated explanantions
  Additional workload for faculty
Scope: Create separate introduction videos for researchers and faculty based on the unit meeting guide and template; Base both videos on the Unit Researcher Guide and present the info in a concise 2-3 minute format
Intended Outcome: Consistent onboarding experience coupled with reduced advisor workload and clear expectations for researtchers and faculty
Stakeholders: HAAG researchers, Faculty advisors, Computational advisors and Future unit managers

## Slide 3: Work Completed
Summarize the major activities, deliverables, procedures, or resources the group produced during the semester.
Deliverables
Documentation
Reviewed the existing Unit Researcher Guide
Faculty Resources
Faculty onboarding PowerPoint
Faculty narration script
Facutly onboarding video
Researcher Resources
Created a researcher onboarding PowerPoint
Researcher narration script
Researcher onboarding video

## Slide 4: Procedure Development
Explain any processes or procedures the team created, why they were needed, and how future HAAG members should use them.
Procedure Created
Faculty Onboarding Process
Introduce why unit meetings exist
Explain advisor responsibilities
Clarify researcher accountability
Direct viewers to the Unit Researcher Guide
Researcher Onboarding Process
Explain the purpose of units.
Explain the roles and responsibilities of researchers, including project representatives and non-attending members.
Provide a more in-depth review of the templates, meeting structure, and working session.
Provide an overview of grading.
These onboarding procedures provide a repeatable process that future HAAG units can reuse when introducing new researchers and advisors.

## Slide 5: Implementation
Describe any procedures that were tested or implemented, who participated, what happened, and what evidence or observations were collected. It is acceptable if implementation was not completed; explain why and what should happen next.
Implementation Status
Full implementation was not completed during the semester due to the limited project timeline and the mid-semester change in initiative scope.
The team shifted its focus toward creating onboarding materials that could be used for future implementation.
Preparation Completed
Faculty and researcher onboarding scripts were developed.
Onboarding PowerPoint presentations were created.
Materials were reviewed and revised based on feedback from Kevin.
Next Steps
Disseminate the onboarding materials to new HAAG members.
Gather feedback from researchers and faculty.
Revise the onboarding resources based on future use.

## Slide 6: Outcomes and Effectiveness
Discuss what worked, what did not work, and how the group evaluated the initiative or its implementation.
What Worked
Separate videos reduce information overload
Faculty receive only information relevant to their role
Researchers receive role-specific onboarding
Videos complement the Unit Researcher Guide
Evaluation
Formal evaluation was not conducted due to time constraints
Future iterations should gather researcher and faculty feedback after onboarding
Future Improvements
Collect feedback after implementation
Update videos as unit procedures evolve
Expand onboarding with additional examples

## Slide 7: Challenges and Adaptations
Identify barriers, changes in scope, scheduling limitations, or decisions that affected the work.
Changes in Scope
Initiative scope changed midway through the semester.
Focus shifted from refining the Unit Researcher Guide and gathering stakeholder feedback to developing separate onboarding videos for researchers and faculty.
Scheduling Limitations
The compressed summer semester limited the time available for implementation and evaluation.
Scope changes required the team to revisit earlier work and adjust project priorities.
Adaptations
Faculty and researcher onboarding materials were developed separately to better address the needs of each audience.
Scripts and presentation materials were revised multiple times as project requirements evolved.

## Slide 8: Reflection and Next Steps
Share the team’s key lessons, remaining gaps, and recommendations for students who may continue the initiative in a future semester
Lessons Learned
Different audiences require different messaging
Faculty onboarding should emphasize mentorship rather than administrative responsibilities.
Short, role specific videos improve accessibility and consistency
Next Steps
Disseminate the onboarding materials to future HAAG researchers and advisors.
Collect feedback to evaluate the effectiveness of the onboarding process after implementation.
Update the videos and Unit Researcher Guide as the unit meeting process evolves.

## Slide 9: Team Contributions
Briefly acknowledge how each group member and supporting admin or former PM researcher contributed.
Minkyung: Made script, slide, and video for researcher side of introduction
Arjun: Made script, slide, and video for faculty side of introduction
Kevin: PM researcher lead, helped with scoping and reviewing the scripts and slides

## Slide 10: Questions & Feedback